## Sheet1
QACINEMAS PROJECT – RISK ASSESSMENT
Risk Description	Source of Risk	What could go wrong	Impact	Likelihood	Responsible	Action
Server goes down	Cloud Provider	Website becomes unreachable	High	Low	Cloud Provider	Ensures to use the right plan for the importance of the software, for example, multi location access when necessary with duplicates backups over the geo locations.
Vulnerability in code	Developers	App could get hacked / data stolen	High	Medium	Developers	Ensure to use a precise and secure language, abiding by the principles, to avoid any code flaws and data leaking where it shouldn’t be accessible
Server Provider gets attacked	Cloud Provider	Important data gets stolen	High	Low	Cloud Provider	Use a cloud provider that offers security protections of your data / client data
Website Stores customer sensitive Information	Developers	Important and unnecessary data gets stored	High	Medium	Developers	Always keep your code up to date with the law regarding the data protection act / GDPR
Payment System gets hacked	Third party Payment Provider	Cards and payments information gets stolen	High	Low	Payment provider	If using a third party payment provider, make sure they abide by the data protection act and are a reputable company with high standard security
Payment System get bypassed	Third party Payment Provider	Bookings do not get paid	Medium	Low	Payment provider	Make sure your payment system works fully, without any flaws to bypass it, so people aren’t able to get a booking for free
Showings get rescheduled	Cinema Staff	Customers have outdated booking information	Low	High	Cinema Staff and Developers	Make sure the right information is displayed on the website, according to the cinema showings, and if any last minute change, implement a change on the website as soon as possible, rebooking customers and emailing them as necessary
About page displays outdated information	Cinema Staff	Customers goes to wrong place, or cannot contact cinema	Low	Medium	Cinema Staff and Developers	Cinema Staff keeps the website updated of any contact changes contacting developers so they can change the relevant info
Descriptions does not match movie	Developers	Customers gets no interest in movie, or wrong interest in a movie they won’t like	Low	Low	Developers	Make sure the right movie description is being added to a movie, so the customers can choose a movie based on their interests
Customers are not checked for ID before buying a movie rated 18+	Customers	Customers successfully book for movies they aren’t supposed to book	High	Medium	Cinema Staff and Developers	Make sure the third party payment system matches ID and card information, so a customer get properly ID checked and as a security measure, for all movies 18+ cinema staff should check for ID before entering the session
General public access 18+ movies pages	Developers	Customers view sensitive or 18+ information they weren’t supposed to	Medium	High	Developers	Make sure the website requires a registration and check of ID before viewing any 18+ sensitive information for movies
Code breaks after an update	Developers	Website stops working, or work in a unintended way	Medium	Medium	Developers	Using version control systems, so every changes can be reverted to a previous state backup, and the continuous integration can be corrected without impacting the service
Customers buy a booking with a fake card	Third party Payment Provider	Customers won’t pay for a showing	Medium	Low	Developers	Make sure to use a third party payment system provider that accept liability for a payment, in case a fake card is used, so they will take responsibility for it
Website and app aren’t provided on time / finished on time	Developers	Cinema could get a delay of start its operations, or lose revenue	High	Low	Developers	Using a SCRUM meeting every morning, so we can keep track of any blockers, or anything impeding the work, make sure to communicate with your developer team really clearly with precise information
Showing is overbooked	Cinema Staff / Developers	Customers cannot get a seat while having a valid booking	High	Medium	Cinema Staff and Developers	Make sure website and cinema software “talk to each other”, so that the cinema staff cannot sell a seat after it being bought by a customer online